## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Arvind | 2026-01-12 | Preprocessing workflow fails to remove specific special characters from unstructured email text, leaving too much noise before inference. | Sprint 1 | Prince | Data Preprocessing | Updated the normalization script to filter out complex signature blocks and non-standard punctuation. | 2026-01-13 | Closed | Significantly reduced noise; the cleaned text is much easier for the model to process.
2 | Prince | 2026-01-22 | Zero-Shot Classification system misclassifies emails when the sender uses highly ambiguous language or sarcasm. | Sprint 2 | Prince | ML Inference / Accuracy | Adjusted the prompt and context window fed into the Zero-Shot model to better understand contextual intent. | 2026-01-24 | Closed | Intent recognition accuracy improved for edge-case emails.
3 | Anne | 2026-01-28 | Data pipeline crashes during the normalization phase when an email contains only an attachment and no body text. | Sprint 2 | Prince | Logic Error | Added a condition to check for empty unstructured text and assign a default "Attachment Only" tag before model inference. | 2026-01-30 | Closed | Pipeline now safely bypasses empty emails without throwing errors.
4 | Ashwin | 2026-02-10 | The model takes too long to classify batches of emails, slowing down the end-to-end workflow. | Sprint 3 | Prince | Performance | Optimized the data preprocessing workflow to batch-process unstructured text before sending it to the ML model. | 2026-02-12 | open | Inference speed has improved, but still monitoring to see if further noise reduction helps speed it up more.
5 | Hemanth | 2026-02-17 | Zero-shot model occasionally routes "Out of Office" auto-replies to the IT Support category instead of filtering them out. | Sprint 4 | Prince | ML Logic Error | Added a specific intent category for "Automated Replies" so the model contextually understands to ignore them. | 2026-02-18 | open | Currently testing the new category against a dataset of 50 auto-replies.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others